## Key & Assumptions
Data | Description | Valid Entries
Org | The Organization that uses the IT product or service | Borough, Township, Shared - Boro host, Shared - Twp host, Consolidated
Dept | The Department that uses the IT product or service
Item | Description of IT product or service
Point of Contact | The Point of Contact in the Department
Type | The type of IT product or service | Support, Software, Hardware, Infrastructure, Management
Priority | The Priority (importance) of the item, it's mission criticality | A, B, C
Urgency | The Urgency (timing) for addressing the item | Now, Pre-Consolidation, Post-Consolidation
Status | The currect Status of the item | New, Analysis, Proposal (Ready for TTF), Pending Task Force, Pending Governing Bodies, Work-in-Progress, Complete
Current Product / Supplier | The name of the Current Product and its Supplier when acquired
Current Service Provider | The name of the Current Service Provider
Current Service Strategy | The Current Service Strategy | In-house, Not Contract, Outsource - Item, Outsource - Bundle, Shared Services, Retire
Proposed Product / Supplier | The name of the Proposed Product and its Supplier
Proposed Service Provider | The name of the Proposed Service Provider
Proposed Service Strategy | The Proposed Service Strategy | In-house, Not Contract, Outsource - Item, Outsource - Bundle, Shared Services, Retire
Proposed Bundle | Indicator to group items into a bundle if the Service Strategy is Outsource - Bundle
Action Plan | The actions plan to get from the current to the proposed
User / Data Migration | Indicator of the relevance for User and/or Data Migration | Yes, No
Location Change | Indicator of the relevance for being relocated with users | Yes, No
Cost | Annual Maintenance Cost
Fitness | Indicator of the capability of the existing item to meet the users needs | High, Medium, Low
Comment | Comments related to the item
Long Term Strategy | The planned long term Service Strategy | In-house, Outsource - Item, Outsource - Bundle, Shared Services, Retire
New Product / Service | Proposed New Product if not one of the Current Products
New Provider | Proposed New Service Provide if not one of the Current Service Providers
Assumptions
Inventory excludes Police Department
Inventory excludes Shared Services Department

## Inventory
Org | Dept | Item | Point of Contact | Type | Pri | Urg | Status | Product / Supplier | Service Provider | Service Strategy | Prop Bundle | Action Plan | Data Migr | Locn | Annual Cost | Fit | Comments and Notes | Long Term Strategy
B | IT | IT Services Management | Hough | Mgmt | A | Pre | WIP |  | mindShift | Out-Bundle |  |  | N |  | 0 |  | Hough is the Boro IT Coordinator, but outsourced to mindShift
T | IT | IT Services Management | McQueen | Mgmt | A | Pre | WIP |  |  | In-house |  |  | N |  | 0
C | IT | IT Services Management |  | Mgmt | A | Pre | WIP |  |  | In-house |  |  | N |  | 0
B | IT | IT Consulting - On Demand | Hough | Support | A | Now | WIP |  | mindShift | Out-Bundle | A |  | N | N | 0 | Hi
T | IT | IT Consulting - On Demand | McQueen | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N | 0 | Hi
C | IT | IT Consulting - On Demand |  | Support | A | Now | WIP |  | CMIT | Out-Bundle | A | Prepare bundle | N | N | 0 | Hi | Revised Scope: HW/SW/INFR - to seek proposals
B | IT | On-site Support - Scheduled | Hough | Support | A | Now | WIP |  | mindShift | Out-Bundle | A |  | N | N | 0 | Hi
T | IT | On-site Support - Scheduled | McQueen | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N | 0 | Hi
C | IT | On-site Support - Scheduled |  | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N | 0 | Hi | Under Consideration by Tech Subcommittee
B | IT | On-site Support - On Demand | Hough | Support | A | Now | WIP |  | mindShift | Out-Bundle | A |  | N | N | 0 | Hi
T | IT | On-site Support - On Demand | McQueen | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N | 0 | Hi
C | IT | On-site Support - On Demand |  | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N | 0 | Hi | Under Consideration by Tech Subcommittee
B | IT | IT Support Access | Hough | Support | A | Now | WIP | Kaseya | mindShift | Out-Bundle | A |  | N | N | 0 |  | Maintenance costs included
T | IT | IT Support Access | McQueen | Support | A | Now | WIP | Go To Assist | Go To Assist | Out-Item | A | Retire | N | N | 3204 | Hi
C | IT | IT Support Access |  | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N |  | Hi
B | IT | IT Help Desk Remote Support | Hough | Support | A | Now | WIP | Kaseya | mindShift | Out-Bundle | A |  | N | N | 0 |  | Maintenance costs included
T | IT | IT Help Desk Remote Support | McQueen | Support | A | Now | WIP | LogMeIn | LogMeIn | Out-Item | A | Retire | Y | N | 1199 | Hi | Retire in favor of Outsource provider
C | IT | IT Help Desk Remote Support |  | Support | A | Now | WIP |  | CMIT | Out-Bundle | A |  | Y | N
B | Finance | Accounting - General ledger | Webb | SW | B | Pre | TTF | Edmunds | Edmunds | Out-Item |  |  | Y |  | 7194 |  | Bundle Tax Collection, GL?
T | Finance | Accounting - General ledger | Monzo | SW | B | Pre | TTF | Municipal SW | Municipal SW | Out-Item |  |  | Y |  | 6744 | Hi | Bundle Tax Collection, GL?
C | Finance | Accounting - General ledger |  | SW | B | Pre | TTF | Edmunds | Edmunds | Out-Item |  |  | Y |  | 7194 |  | No upfront costs- ceiling training $2,400
B | Tax Collection | Tax Collection Management SW | Webb | SW | B | Pre | TTF | Vital | Vital | Out-Item |  |  | Y | N | 3835 |  | Bundle Tax Collection, GL?
T | Tax Collection | Tax Collection Management SW | Monzo | SW | B | Pre | TTF | First Byte | First Byte | Out-Item |  |  | Y | N | 3235 | Low | Bundle Tax Collection, GL?
C | Tax Collection | Tax Collection Management SW |  | SW | B | Pre | TTF | First Byte | First Byte | Out-Item |  |  | Y | N |  |  | Bundle did not make sense
B | Tax Collection | Tax Collection Web Interface | Webb | SW | B | Pre | Analysis | Citenet | Citenet | Out-Item |  | Retire | N | N | 2500
T | Tax Collection | Tax Collection Web Interface | Monzo | SW | B | Pre | Analysis | Citenet | Citenet | Out-Item |  |  | N | N | 4000 | Hi | Is there an incremental cost?
C | Tax Collection | Tax Collection Web Interface |  | SW | B | Pre | Analysis | Citenet | Citenet | Out-Item |  |  | N | N
S-T | Tax Assessment | Tax Assessments Records Mgt | Snyder | SW | B | Pre | WIP | Vital | Vital | Out-Item |  |  | Y |  | 6567 |  | Data migration requirements for consolidation |  | 12000?
C | Tax Assessment | Tax Assessments Records Mgt |  | SW | B | Pre | WIP | Vital | Vital | Out-Item |  | New tax maps in September. Vital to handle all aspects of conversion. No incremental cost -- to be confirmed. | Y |  | 9000 |  | Data migration requirements for consolidation
B | HR | Time & Attendance Records | ? | SW | B | Pre | Analysis | Microsoft Access | None | In-house |  | Need point of contact in borough | Y | N |  | Low | Data migration requirements for consolidation
T | HR | Time & Attendance Records | Colquhoun | SW | B | Pre | Analysis | Visual Comp Solutions | Visual Comp Solutions | Out-Item |  |  | N | N | 5174 | Hi
C | HR | Time & Attendance Records |  | SW | B | Pre | Analysis | [5 empty] | N | N |  | Hi
B | Court | Court Management System | Shapiro | SW | C | Pre | WIP | ? | State of NJ | Shared Svc |  | State to Consolidate records | Y | Y |  |  | Consolidation of records into new Muncipality
T | Court | Court Management System | Sliker-Monda | SW | C | Pre | WIP | ? | State of NJ | Shared Svc |  | State to Consolidate records | Y | Y |  | Hi | Consolidation of records into new Muncipality
C | Court | Court Management System |  | SW | C | Pre | WIP | ? | State of NJ | Shared Svc |  | State to Consolidate records | Y | Y |  | Hi | Consolidation of records into new Muncipality
B | Engineering | Geographic Info Sys (GIS) | West | SW | C | Post | WIP | ESRI-Arch GIS | ESRI-Arch GIS | Out-Item |  | No Change | Y |  | ? |  | License to remain same for 2012, convert in 2013
T | Engineering | Geographic Info Sys (GIS) | Kiser | SW | C | Post | WIP | DLT Solutions | DLT Solutions | Out-Item |  | No Change | Y |  | 4028 | Hi | License to remain same for 2012, convert in 2013
C | Engineering | Geographic Info Sys (GIS) |  | SW | C | Post | WIP |  |  | Out-Item |  | No Change | Y |  |  | Hi
B | Construction | Construction Management | Vogt | SW | B | Pre | Analysis | Mitchell Humphrey | Mitchell Humphrey | Out-Item |  | Retire Boro. Need to obtain cost estimate for Conversion | Y |  | ? | Hi | Merge into Township db
T | Construction | Construction Management | Pettenati | SW | B | Post | Analysis | Mitchell Humphrey | Mitchell Humphrey | Out-Item |  | Retain | N |  | 2070 | Hi
C | Construction | Construction Management |  | SW | B | Post | Analysis | Mitchell Humphrey | Mitchell Humphrey | Out-Item |  | Some complexities in migration need to be addressed. Proposal is coming from Mitchell Humphrey - end of june. | N |  |  | Hi | Continue with existing provider
B | Clerk | Dog Licensing Management | Bruschi | SW | B | Pre | WIP | Microsoft Access | None | In-house |  | Retire | Y | N | 0 |  | Municipal software will perform data migration of 300 dogs at no charge
T | Clerk | Dog Licensing Management | McDermott | SW | B | Pre | WIP | Municipal SW | Municipal SW | Out-Item |  |  | Y | N | 408 | Hi
C | Clerk | Dog Licensing Management |  | SW | B | Pre | WIP | Municipal SW | Municipal SW | Out-Item |  | Municipal SW to handle data transfer before yearend. | Y | N | 408 | Hi
B | IT | Antivirus / Spyware Detection | Hough | SW | C | Now | WIP | Hosted | mindShift | Out-Bundle | A |  | N | N | 0 |  | Maintenance costs included
T | IT | Antivirus / Spyware Detection | McQueen | SW | C | Now | WIP | Viper | Viper | Out-Item | A |  | N | N | 1855 | Hi
C | IT | Antivirus / Spyware Detection |  | SW | C | Now | WIP |  | CMIT | Out-Bundle | A |  | N | N |  | Hi
B | IT | Spam | Hough | SW | C | Now | WIP | MXLogix | mindShift | Out-Bundle | A |  | N | N | 0 |  | Maintenance costs included
T | IT | Spam | McQueen | SW | C | Now | WIP | Barracuda | Barracuda | Out-Item | A |  | Y | N | 760 | Hi
C | IT | Spam |  | SW | C | Now | WIP | Barracuda | Barracuda | Out-Item | A |  | Y | N | 760 | Hi | Retain Barracuda in addition to bundled service, expire 2013
B | IT | Web Filter | Hough | SW | C | Now | WIP | MXLogix | mindShift | Out-Bundle | A |  | N | N | 0 |  | Maintenance costs included
T | IT | Web Filter | McQueen | SW | C | Now | WIP | Barracuda | Barracuda | Out-Item | A |  | Y | N | 1600 | Hi
C | IT | Web Filter |  | SW | C | Now | WIP | Barracuda | Barracuda | Out-Item | A |  | Y | N |  | Hi | Retain Barracuda in addition to bundled service, expire 2016
B | Clerk | Website Hosting / Maintenance | Bruschi | SW | B | Pre | WIP | N/A | Princeton Online | Out-Item |  |  | Y | N | 3075
T | Clerk | Website Hosting / Maintenance | McDermott | SW | B | Pre | WIP | N/A | City Connections | Out-Item |  |  | Y | N | 6929 | Hi
C | Clerk | Website Hosting / Maintenance |  | SW | B | Pre | WIP | N/A | City Connections | Out-Item |  | Princeton Online declined. | Y | N | 9199 |  | Consider existing and/or new providers
B | IT | Email | Hough | SW | B | Pre | WIP | MS Outlook Exchange | mindShift | Out-Bundle |  | Retire | Y | N | 9000
T | IT | Email | McQueen | SW | B | Pre | WIP | First Class | First Class | Out-Item |  |  | N | N | 3300 | Hi
C | IT | Email |  | SW | B | Pre | WIP | First Class | First Class | Out-Item |  | Conversion at year end | N | N | 4476 | Hi | Taking proposal to TTF on 5/2. Add $1176 pa for Boro plus onetime license fee $5635
S-B | Health | Birth Records Management | Henry | SW | C | Pre | WIP | Munidex | ? |  |  |  | Y |  | 540 |  | Consolidation of records into new Muncipality
C | Health | Birth Records Management |  | SW | C | Pre | WIP | Munidex | ? |  |  | Need to have subcomm person speak to Henry | Y |  | 540 |  | Consolidation of records into new Muncipality
B | Finance | Payroll Management | Webb | SW | B | Pre | TTF | ADP | ADP | Out-Item |  |  | Y |  | 9626
T | HR | Payroll Management | Colquhoun | SW | B | Pre | TTF | Primepoint | Primepoint | Out-Item |  |  | Y |  |  | Med
C | HR | Payroll Management |  | SW | B | Pre | TTF | Primepoint | Primepoint | Out-Item |  |  | Y |  |  | Med
S-B | Fire | Fire Management System | Drake | SW | C | Pre | Comp | Laptop Air Cards | ? | In-house |  |  | N |  | 4800
C | Fire | Fire Management System |  | SW | C | Pre | Comp | Laptop Air Cards | ? | In-house |  | Hough should follow up with Drake about remaining tasks, costs. Issue: location move, if any. | N |  | 4800
S-B | Fire | Fire Inspections | Drake | SW | C | Pre | Comp | Firehouse | ? |  |  |  | N |  | 1458
C | Fire | Fire Inspections |  | SW | C | Pre | Comp | Firehouse | ? |  |  | Hough should follow up with Drake about remaining tasks, costs. Issue: location move, if any. | N |  | 1458
B | Engineering | CAD Software | Knigge | SW | C | Post | WIP | Autodesk | Autodesk | Out-Item |  | No action required until post Consolidation | Y |  |  |  | Infrastructure Design Suite 2013 Standard and Premium, License to remain same for 2012, convert in 2013
T | Engineering | CAD Software | Kiser | SW | C | Post | WIP | Autodesk | Autodesk | Out-Item |  | No action required until post Consolidation | Y |  |  | Hi | AutoCAD Civil 3D, AutoCAD Raster Design, License to remain same for 2012, convert in 2013
C | Engineering | CAD Software |  | SW | C | Post | WIP | Autodesk | Autodesk | Out-Item |  | No action required until post Consolidation | Y |  |  | Hi | AutoCAD Civil 3D, AutoCAD Raster Design, License to remain same for 2012, convert in 2013
B | Clerk | Boards and Commissions | Delores | SW | C | Post | WIP | ? | ? | In-house |  |  | Y |  | 0 |  | Microsoft Access is DH recommendation
T | Clerk | Boards and Commissions | McDermott | SW | C | Post | WIP | Microsoft Access | In-house | In-house |  |  | Y |  |  | Med | Microsoft Access is DH recommendation
C | Clerk | Boards and Commissions |  | SW | C | Post | WIP | Microsoft Access | In-house | In-house |  |  | Y |  |  |  | Microsoft Access is DH recommendation
B | Clerk | Parking Permits | Delores | SW | B | Pre | WIP | Microsoft Access | In-house | In-house |  |  | Y |  | 0 |  | Microsoft Access is DH recommendation
T | Clerk | Parking Permits | McDermott | SW | B | Pre | WIP | Microsoft Word | In-house | In-house |  |  | Y |  |  | Med | Microsoft Access is DH recommendation
C | Clerk | Parking Permits |  | SW | B | Pre | WIP | Microsoft Access | In-house | In-house |  |  | Y |  |  |  | Microsoft Access is DH recommendation
B | Clerk | Resolutions | Delores | SW | C | Post | WIP | Microsoft Word | In-house | In-house |  |  | Y |  | 0 |  | Microsoft Word is DH recommendation
T | Clerk | Resolutions | McDermott | SW | C | Post | WIP | Microsoft Word | In-house | In-house |  |  | Y |  |  | Med | Microsoft Word is DH recommendation
C | Clerk | Resolutions |  | SW | C | Post | WIP | Microsoft Word | In-house | In-house |  |  | Y |  |  |  | Microsoft Word is DH recommendation
B | Construction | Records Archiving | ? | SW | B | Post | Analysis | ? | ? | In-house | [6 empty] | Waiting on DH recommendations
T | Construction | Records Archiving | Pettenati | SW | B | Post | Analysis | Alchemy | Alchemy | Out-Item | [5 empty] | Med | Waiting on DH recommendations
C | Construction | Records Archiving |  | SW | B | Post | Analysis |  |  |  |  | Alchemy no longer a state contract vendor. Hough needs to determine Borough product, and game plan. |  |  |  |  | Waiting on DH recommendations
B | IT | Smartphones | Webb | HW | B | Pre | New | ? | ? |  |  |  | Y
T | IT | Smartphones | McQueen | HW | B | Pre | Analysis | Verizon Wireless | Verizon Wireless | Out-Bundle |  |  | N
C | IT | Smartphones |  | HW | B | Pre | Analysis |  |  | Out-Bundle | ? |  | N
B | IT | PC Workstations | Hough | HW | B | Now | WIP |  | mindShift | Out-Bundle | A |  | N |  | 0 |  | 93
T | IT | PC Workstations | McQueen | HW | B | Now | WIP | N/A | In-house | In-house | A |  | N |  | 0 |  | 125
C | IT | PC Workstations |  | HW | B | Now | WIP |  | CMIT | Out-Bundle | A |  | N |  |  |  | 218
B | IT | Departmental Laptops | Hough | HW | B | Now | WIP |  | mindShift | Out-Bundle | A |  | N |  | 0 |  | 18
T | IT | Departmental Laptops | McQueen | HW | B | Now | WIP | N/A | In-house | In-house | A |  | N |  | 0 |  | 0
C | IT | Departmental Laptops |  | HW | B | Now | WIP |  | CMIT | Out-Bundle | A |  | N |  |  |  | 18
B | IT | Printers | Hough | HW | B | Now | WIP |  | mindShift | Out-Bundle | A |  | N |  | 0 |  | 35
T | IT | Printers | McQueen | HW | B | Now | WIP | N/A | In-house | In-house | A |  | N |  | 0 |  | 75
C | IT | Printers |  | HW | B | Now | WIP |  | CMIT | Out-Bundle | A |  | N |  |  |  | 110
B | IT | Fax Machines | Hough | HW | B | Now | WIP |  | mindShift | Out-Bundle | A |  | N |  | 0 |  | 10
T | IT | Fax Machines | McQueen | HW | B | Now | WIP | N/A | In-house | In-house | A |  | N |  |  |  | 15
C | IT | Fax Machines |  | HW | B | Now | WIP |  |  | Out-Bundle | A |  | N |  |  |  | 25
B | IT | Phone System | Hough | HW | A | Pre | WIP | Avaya | ? | Not Contract |  | Retire | Y |  | 3700
T | IT | Phone System | McQueen | HW | A | Pre | WIP | Mitel | VOIP Systems | Out-Item |  |  | Y |  | 11348 | Hi
C | IT | Phone System |  | HW | A | Pre | WIP | Mitel | VOIP Systems | Out-Item |  | VOIP to sign contract and establish timeline. Likely to convert before yearend. At least 3 month project. | Y
B | IT | Building Security - Doors | Hough | HW | B | Pre | Analysis | Honeywell | ? | Out-Item |  | No Change | Y | N | 0 |  | Is this out-item or in-house, since no contract?
T | IT | Building Security - Doors | McQueen | HW | B | Pre | Analysis | Enforce Concepts | All Secure Locks | Out-Item |  |  | Y | N | 4000 | Hi
C | IT | Building Security - Doors |  | HW | B | Pre | Analysis |  |  | Out-Item |  |  | Y | N
B | IT | Building Security - Cameras | Hough | HW | B | Pre | Analysis | Triad Security Systems | Triad Security Systems | Out-Item |  | confirm if only parking garage cameras. | Y | N | 0 |  | Is this out-item or in-house, since no contract?
T | IT | Building Security - Cameras | McQueen | HW | B | Pre | Analysis | Open Systems | Open Systems | Out-Item |  |  | Y | N | 2500 | Hi
C | IT | Building Security - Cameras |  | HW | B | Pre | Analysis |  |  | Out-Item |  | needs more analysis by mcqueen when time is available | Y | N | tbd
B | IT | Rapid Mass Calling System | Hough | HW | B | Pre | WIP | None | None | None |  | Retire | Y | N | 0 |  | Consolidation of records into new Muncipality, no additional cost (price not sensitive to number of users)
T | IT | Rapid Mass Calling System | McQueen | HW | B | Pre | WIP | Rapid Notify | Rapid Notify | Out-Item |  |  | N | N | 9500 | Hi
C | IT | Rapid Mass Calling System |  | HW | B | Pre | WIP | Rapid Notify | Rapid Notify | Out-Item |  |  | N | N | 9500 | Hi
B | IT | Panic Alarm Monitoring | Hough | HW | B | Pre | Analysis | ? | In-house | In-house |  |  | N |  | 0 |  | N/A
T | IT | Panic Alarm Monitoring | McQueen | HW | B | Pre | Analysis | Vector Security | Vector Security | Out-Item |  |  | N |  | 193 | Med
C | IT | Panic Alarm Monitoring |  | HW | B | Pre | Analysis |  |  | Out-Item |  |  | N |  | tbd
B | IT | Network / Server / Switches Monitoring | Hough | Infra | B | Now | WIP | Monitor IT | mindShift | Out-Bundle | A |  | Y |  | 0 |  | Maintenance costs included
T | IT | Network / Server / Switches Monitoring | McQueen | Infra | B | Now | WIP | What's up Gold | What's up Gold | Out-Item | A | Retire | Y |  | 2530 | Low
C | IT | Network / Server / Switches Monitoring |  | Infra | B | Now | WIP | Various | CMIT | Out-Bundle | A |  | Y |  | 0
B | IT | Servers, firewall, backup | Hough | Infra | A | Now | WIP | Various | mindShift | Out-Bundle | A |  | Y |  | 72000 |  | Outsource the combined infrastructure to one provider
T | IT | Servers, firewall, backup | McQueen | Infra | A | Now | WIP | Various | CMIT | Out-Bundle | A |  | Y |  | 63996 | Hi | Outsource the combined infrastructure to one provider
C | IT | Servers, firewall, backup |  | Infra | A | Now | WIP | Various | CMIT | Out-Bundle | A |  | Y |  | 106488 |  | Outsource the combined infrastructure to one provider
|  | Records Management |  | SW |  | Post | New
|  | Maintenance Management System |  | SW |  | Post | New

## Validation
Org | Type | Priority | Urgency | Status | Strategy | Fitness
B | Support | A | Now | New | In-house | Hi
T | SW | B | Pre | Analysis | Not Contract | Med
S-B | HW | C | Post | Proposal | Out-Item | Low
S-T | Infra |  |  | TTF | Out-Bundle
C | Mgmt |  |  | Gov Bod | Shared Svc
|  |  |  | WIP | Retire
|  |  |  | Compl | None