## TTF ONGOING TASKS
Priority Task Inventory (Outstanding Tasks) ¦ Princeton Transition Task Force (TTF) |  | Transition Task Force Action Item
Last Updated 30 July 2012 |  | Governing Bodies Action Item
| Mar |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Full Transition Task Force
Monitor progress against remaining deliverables in subcommittees (as shown below)
Ongoing oversight of subcommittee work; manage inter-committee communication; monitor Gov Body progress
DELIVERABLE: Regular reporting at TTF; hold subcommittee chairs accountable for timelines
IN PROCESS: RESPONSIBILITY OF TASK FORCE
2. Infrastructure and Operations
2d. Bid process for townwide garbage collection; determine service level | [5 empty] | *RFB*
Review bids and options for service level
STATUS: Initial steps done to permit bid solicitation; Additional review after bids are received
TTF TASK COMPLETED (INITIAL - ADDITIONAL REVIEW MAY BE REQUIRED)
3. Facilities and Other Assets
3c. Review of required modifications and schedule estimates for existing facilities
To be determined
STATUS: Phase 2 study to implement recommendations re: facility and office deployment
IN PROCESS: RESPONSIBILITY OF TASK FORCE (or Administrators?)
5. Boards, Committees and Commissions
5b. Recommendation on status, membership, apppointment of BCCs
Develop process for populating BCCs as soon as practicable post-consolidation
STATUS: Many completed already; remaining group in process
IN PROCESS: RESPONSIBILITY OF TASK FORCE
5c. Determination of framework for Advisory Planning Districts
Develop process for establishing and populating APDs as soon as practicable post-consolidation
STATUS: Still considering models/approaches
IN PROCESS: RESPONSIBILITY OF TASK FORCE
6. Communications and Outreach
6a. Ensure effective process and access for all TTF / Subcommittee work
Monitor communications process re: agendas, minutes, public notices of meetings, etc.
STATUS: Ongoing w/ regular reporting at TTF; Website; Q&A repository on website; "Final" report oversight
IN PROCESS: RESPONSIBILITY OF TASK FORCE w/ CGR
6b. Public forums to update residents on process
Organize and facilitate periodic public forums to inform community, solicit feedback
STATUS: Public forum in the fall coincident w/ "Final" report
IN PROCESS: RESPONSIBILITY OF TASK FORCE
6c. Leverage community events / organizations to convey information
Organize and facilitate smaller presentations to neighborhood groups, community organizations
STATUS: Ongoing
IN PROCESS: RESPONSIBILITY OF TASK FORCE
6d. Capture excitement and history with a celebration of the consolidated Princeton
Plan celebration for Jan 1, 2013
STATUS: Ongoing
IN PROCESS: RESPONSIBILITY OF TASK FORCE
6e. Capture changes for the new administration
Notifications to MLS, mapping companies, etc.
STATUS: Ongoing
IN PROCESS: RESPONSIBILITY OF TASK FORCE
7. Information Technology
7d. Facility aspects of resource integration plan
Develop draft plan for IT deployment, hardware location, etc.
STATUS: Some deployment solutions will be location-dependent; Bob McQueen leading plan; Draft plan by 8/1
IN PROCESS: RESPONSIBILITY OF TASK FORCE, THEN GOVERNING BODIES
8. Finance
8a. Monitor implementation plans vs. savings estimates
Documentation of TTF-recommended plans and associated savings/costs
STATUS: Ongoing; issue summary report mid-fall
IN PROCESS: RESPONSIBILITY OF TASK FORCE
8b. Track transition costs / liaison w/ state re: reimbursement
Document all implementation costs; establish process for reimbursement
STATUS: Establish state funding process mid-Sept; issue summary report at year-end
IN PROCESS: RESPONSIBILITY OF TASK FORCE
9. Legal
9a. Attorneys and PERC: Integration of CBAs
Integration of police and public works contracts
STATUS: Ongoing; Regular updates from administrators
IN PROCESS: RESPONSIBILITY OF P.E.R.C., LEGAL COUNSEL AND GOVERNING BODIES

## TTF COMPLETED TASKS
Priority Task Inventory (Completed Tasks) ¦ Princeton Transition Task Force (TTF)
Last Updated 30 July 2012
| Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug | Sep | Oct | Nov | Dec
Full Transition Task Force
Establish process for appointing "Day One" personnel at strategic positions | [5 empty] | XX | XX
Designate "Day One" administrator, police chief, engineer, DPW chief, CFO, clerk, const official, tax collector
TTF TASK COMPLETED
1. Personnel
1a. Workforce sizing options (severance/ERI options, impacts) | [5 empty] | XX | XX
Develop summary of options and preliminary cost analysis based on assumptions and state guidance
TTF TASK COMPLETED
1b. Develop process recommendations for personnel selection at strategic positions | [5 empty] | XX | XX
Process recommendation
TTF TASK COMPLETED
1c. Organizational structure (proposed reconfigurations) |  |  |  |  | XX | XX
Vet proposals for Admin/Finance, Cmty Services, Court, Affordable Housing; make recommendation
TTF TASK COMPLETED
1d. Reconcile employee benefits (health, PTO, empl manuals) | [8 empty] | XX | XX
Document Boro/Twp differences in benefits and policies; make recommendation on intergration
TTF TASK COMPLETED
1e. State actuarial analysis of ERI eligibility and impact (if necessary) | XX | XX |  |  |  |  | <-- Determined to not be required
DCA/PERS/PFRS complete an analysis on ERI options and costs; recommendation on option(s)
TTF TASK COMPLETED
1f. Promotion of cross-pollination |  |  | XX | XX | XX | XX
Encourage Boro/Twp departments to "shadow" one another during 2012, report on progress
TTF TASK COMPLETED
1g. Review of salary differentials | [8 empty] | XX | XX
Determine reconciliation processes
TTF TASK COMPLETED - Administrators following up
1h. Merging of union contracts | [8 empty] | XX | XX
Monitor contract integration process
TTF TASK COMPLETED - PERC taking lead w/ Administrators following up
2. Infrastructure and Operations
2a. Organizational structure (reporting, dept framework) |  |  |  |  | XX | XX
Vet proposal for Public Works, Engineering, PSOC, etc., make recommendation
TTF TASK COMPLETED
2b. Review service level options for brush / leaves / composting | [6 empty] | XX | XX
Consider current service level differences (Boro/Twp/denser areas); make recommendation
TTF TASK COMPLETED
2c. Recommendation re: facilities | [6 empty] | XX | XX
Vet proposals for housing consolidated DPW; make short-range recommendation
TTF TASK COMPLETED
2e. Integration of capital improvement plans | [6 empty] | XX | XX
Develop draft CIP and equipment replacement plan for consolidated department
TTF TASK COMPLETED
3. Facilities and Other Assets
3a. Inventory of existing facilities and assets | [5 empty] | XX | XX
Document all existing facilities, space, utilization and condition
TTF TASK COMPLETED
3b. Recommendation re: deploying municipal offices | [8 empty] | XX | XX
Using KSS findings, recommend allocation of space for muni functions; identify surplus opportunities
TTF TASK COMPLETED
4. Public Safety
4a. Organizational structure issues (integration for "Day One") | [6 empty] | XX | XX
Organizational structure and size
TTF TASK COMPLETED
4b. Recommendation re: facilities |  |  |  |  | XX | XX
Recommendation for housing PD in current Township PD headquarters
TTF TASK COMPLETED
4c. Integration of SOPs / protocols | [8 empty] | XX | XX
Integration of procedures, protocols, accreditation-related, etc.
TTF TASK COMPLETED
4d. Recommendations re: police IT issues (incl. dispatch) | [7 empty] | XX | XX
Determine equipment to be integrated, make recommendation
TTF TASK COMPLETED
4e. Recommendations re: integrating capital / equip / firearms | [7 empty] | XX | XX
Determine equipment to be integrated, make recommendation re: need and timing
TTF TASK COMPLETED - Department taking lead w/ Administrators following up
4f. Interaction of PD with University Public Safety | [7 empty] | XX | XX
Identify options, consider opportunities
TTF TASK COMPLETED
5. Boards, Committees and Commissions
5a. Inventory of existing BCCs |  |  |  |  | XX | XX
Document current boards, committees and commissions, their sizes and methods of appointment
TTF TASK COMPLETED
7. Information Technology
7a. Inventory existing hardware, software, vendor support |  |  | XX | XX
Document all existing
TTF TASK COMPLETED
7b. Resource integration plan - general | [6 empty] | XX | XX | XX | XX
Develop draft plan for integrating general IT (e.g. servers, software suites, printers, switches, etc.)
(includes phone system, email, dog licensing, clerk's office document mft for resolutions, parking permits, IT
consultant, website design/maintenance, general ledger and tax)
TTF TASK COMPLETED
7c. Resource integration plan - police, other specialized ‡ | [7 empty] | XX | XX
Develop draft plan for integrating IT (e.g. dispatch, 911, CAD, MDTs, records mgt, evidence, prints)
TTF TASK COMPLETED
8. Finance
8c. Preliminary draft combination of budget |  |  |  |  | XX | XX
After approval of 2012 Boro/Twp budgets, develop a draft integrated budget
TTF TASK COMPLETED
8d. Consideration of sewer rates, open space tax rate-setting process | [6 empty] | XX | XX
Documentation of required process and rate options
TTF TASK COMPLETED
8e. Monitor debt combination process |  |  | XX | XX |  |  |  |  | <-- Determined to not be required
Facilitate work by FAs, bond counsel, etc. to combine and transfer debt obligations
TTF TASK COMPLETED
9. Legal
9b. Attorneys, FAs and Bond Counsel: Debt Combination Process |  |  | XX | XX |  |  |  |  | <-- Determined to not be required
Combine and transfer debt obligations from Boro/Twp to new municipality (as necessary)
TTF TASK COMPLETED